{"text_format":"1","workbook":"xlsx","n_sheets":4,"sheets":["Cover","Report","Footnotes","Disclaimers&Definitions "],"not_rendered":{"charts":0,"images":4,"macros":0,"external_links":0,"defined_names":17,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Cover","index":0,"n_rows":11,"n_cols":1,"rows_kept":11,"cut":false,"hidden":false,"merged":[]}
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[" "]

{"sheet":"Report","index":1,"n_rows":42,"n_cols":18,"rows_kept":42,"cut":false,"hidden":false,"merged":[[2,0,2,12],[3,0,3,12],[4,14,4,17],[6,14,6,17]]}
[]
["Updated: February 17, 2015"]
["Revisions Noted in Bold"]
["Dynamically positioned «"]
[null,null,null,null,null,null,null,null,null,null,null,"Dayrate on","Dayrate on",null,"Estimated Out of Service Days (4)"]
[null,null,null,null,"Yr. (1)","Water","Drilling ",null,null,"Estimated","Estimated","Current","Previous"]
[null,"Footnote ","Floater","Dynamically","Entered","Depth","Depth",null,null," Contract","Expiration","Contract (3)","Contract (3)",null,2015]
["Rig Type/Name","References","Type","Positioned","Service","(Feet)","(Feet)","Location","Customer","Start Date (2)"," Date (2)","(Dollars)","(Dollars)",null,"Q1","Q2","Q3","Q4"]
[]
["Rigs Under Construction"]
[]
["Transocean Cepheus",-9,null,null,"TBA",400,35000,"TBA"]
["Transocean Cassiopeia",-9,null,null,"TBA",400,35000,"TBA"]
["Transocean Centaurus",-9,null,null,"TBA",400,35000,"TBA"]
["Transocean Cetus",-9,null,null,"TBA",400,35000,"TBA"]
["Transocean Circinus",-9,null,null,"TBA",400,35000,"TBA"]
[]
["High Specification Floater: Ultra-Deepwater "]
[]
["Discoverer Inspiration","(6), (11)","ship","«",2010,12000,40000,"USGOM","Chevron","2010-02-01","2015-03-27",523000,494000,null,21,0,0,0]
[null,"(6), (8), (11)",null,null,null,null,null,"USGOM","Chevron","2015-03-30","2020-03-31",585000,523000]
["Discoverer Deep Seas",-6,"ship","«",2001,10000,35000,"USGOM","Murphy Oil","2013-10-31","2016-11-30",608000,456000,null,0,60,12,0]
["Discoverer Enterprise",null,"ship","«",1999,10000,35000,"USGOM","BP","2014-12-21","2015-02-28",399000,615000,null,0,0,0,0]
["GSF C.R. Luigs",null,"ship","«",2000,10000,35000,null,null,null,"Idle",null,null,null,29,0,0,0]
["Deepwater Nautilus","(6), (8)","semi",null,2000,8000,30000,"USGOM","Shell","2012-08-01","2017-08-01",531000,551000,null,6,91,37,0]
["Sedco Express","(6)","semi","«",2001,7500,35000,"Nigeria","CAMAC","2014-12-27","2015-02-28",300000,"N/A",null,0,0,0,0]
[]
["High Specification Floater: Deepwater"]
[]
["Sedco 706"," (6), (7), (8)","semi","«","1976/1994/ 2008",6500,25000,"Brazil","Petrobras","2014-05-01","2016-09-01",290000,361000,null,0,60,0,0]
[]
["Midwater Floaters"]
[]
["Transocean Legend",-7,"semi",null,1983,3500,25000,null,null,null,"Idle",null,null,null,0,0,0,0]
["Sedco 712",null,"semi",null,1983,1600,25000,"UKNS","Talisman","2014-10-01","2015-04-01",391000,386000,null,28,0,0,0]
[null,null,null,null,null,null,null,"UKNS","Talisman","2015-04-01","2015-10-01",397000,391000]
[null,null,null,null,null,null,null,"UKNS","Talisman","2015-10-01","2016-04-01",403000,397000]
[null,null,null,null,null,null,null,"UKNS","Talisman","2016-04-01","2016-10-01",409000,403000]
[]
["High Specification Jackups"]
[]
["GSF Galaxy III",null,null,null,1999,400,30000,"Denmark","Maersk","2014-11-18","2015-03-31",175000,160000,null,0,0,0,0]

{"sheet":"Footnotes","index":2,"n_rows":17,"n_cols":3,"rows_kept":17,"cut":false,"hidden":false,"merged":[[15,2,15,13],[16,2,16,12],[17,2,17,13],[4,1,4,2],[8,2,8,13],[6,2,6,13],[7,2,7,13],[9,2,9,13],[10,2,10,13],[11,2,11,13],[12,2,12,13],[13,2,13,13],[14,2,14,13]]}
[]
[null,{"$f":"Report!A2","v":"Updated: February 17, 2015"}]
[null,{"$f":"Report!A3","v":"Revisions Noted in Bold"}]
[]
[null,"Footnotes"]
["Prev"]
["(1)","(1)","Dates shown are the original service date and the date of the most recent upgrade, if any."]
["(2)","(2)","Estimated Contract Start and Estimated Expiration Dates are calculated as follows: (1) for events estimated to occur between the 1st and 15th of a month, the previous month is reported (i.e. a contract which is estimated to commence on May 4, 2015 will be reported as commencing in April 2015) and (2) for events estimated to occur between the 16th and the end of a month, the actual month is reported (i.e. a contract which is estimated to commence on May 24, 2015 will be reported as commencing in May 2015).  Expiration dates represent the company's current estimate of the earliest date the contract for each rig is likely to expire. Some rigs have two or more contracts in continuation, so the last line shows the estimated earliest availability. Many contracts permit the customer to extend the contract.  "]
["(3)","(3)","Represents the full operating dayrate, although the average dayrate over the term of the contract will be lower and could be substantially lower. Does not reflect incentive programs which are typically based on the rig's operating performance against a performance curve. Please refer to the “Customer Contract Duration and Dayrates and Risks Associated with Operations” section of the Disclaimers & Definitions for a description of dayrates.  This column may not reflect the rate currently being received under the contract as a result of an applicable standby rate or other rate, which typically is less than the contract dayrate."]
["(4)","(4)","The out of service time represents those days where a rig is scheduled to be out of service and not be available to earn an operating dayrate. Please refer to the “Out of Service Days (Shipyards, Mobilizations, Demobilizations, Contract Preparation)” section of the Disclaimers & Definitions for a full description.  "]
["(5)","(5)","Estimated Average Contract Dayrate is defined as the average contracted full operating dayrate to be earned per revenue earning day. See note (3) for definition of full operating dayrate."]
["(6)","(6)","Reflects the current contracted dayrate which could reflect prior cost escalations and could change in the future due to further cost escalations."]
["(7)","(7)","Reflects the current contracted dayrate which, along with costs, includes a foreign currency component.  Changes in the value of the U.S. Dollar relative to certain foreign currencies will result in an adjustment to the dayrate according to the terms of the contract.  The dayrate adjustment generally offsets the foreign currency exchange-related change in costs."]
["(8)","(8)","Current contract provides for a bonus incentive opportunity not reflected in the stated current contract dayrate."]
["(9)","(9)","The first of five newbuild high-specification jackups contracted to Keppel FELS Limited's shipyard in Singapore is expected to be delivered from the shipyard in the third quarter of 2016 and the remaining four jackups delivered at approximately six-month intervals thereafter."]
["(10)","(10)","Fixed price options may be exercised at the customer’s discretion. During periods when dayrates on new contracts are increasing relative to existing contracts, the likelihood of customers’ exercising fixed price options increases. During periods when dayrates on new contracts are decreasing relative to existing contracts, the likelihood of customers’ exercising fixed price options declines."]
[null,"(11)","The rig is owned by Transocean Partners LLC in which the company owns less than a 100% interest. Please refer to Transocean Partners LLC (NYSE: RIGP) Fleet Status Report which can be found at www.transoceanpartners.com."]

{"sheet":"Disclaimers&Definitions ","index":3,"n_rows":3,"n_cols":1,"rows_kept":3,"cut":false,"hidden":false,"merged":[[2,0,2,11]]}
[" "]
[]
["DISCLAIMERS & DEFINITIONS"]